MAIAEDGE NETWORKS  ·  ENGINEERING

Statement of Work

Nexus Multi-Building Connectivity Architecture

Engineering Phase

| DOCUMENT VERSION | v2.0 |
| --- | --- |
| PREPARED BY | MaiaEdge Networks, Inc. (“CONTRACTOR”) |
| PREPARED FOR | Nexus Hubbard Carrier, LLC (“OWNER”). |
| DATE | May 2026 |
| CLASSIFICATION | Confidential & Proprietary |
| DOCUMENT OWNER | MaiaEdge Engineering Lead |

SECTION  01

OBJECTIVE

This Statement of Work (“SOW No.1”) defines the engineering scope required to de-risk the delivery schedule for the initial Phase 1 deployment of 9 Data Halls and 1 Carrier Hotel at Nexus Data Centers located near Hubbard, Texas, while establishing scalable architecture capable of supporting up to 65 Nexus data center buildings across the portfolio.

CONTRACTOR shall:

•  Achieve approximately 60% engineering completion across all design domains;

•  Produce procurement-ready outputs including full Bill of Materials and vendor specifications; and

•  Enable a seamless transition to construction and deployment execution phases.

This SOW covers engineering services only. Procurement execution, physical installation, and construction activities are explicitly excluded unless separately scoped.

SECTION  02

SCOPE OF WORK

2.1  Phase 1 — 9 Data Halls and Carrier Hotel

CONTRACTOR shall develop a Low-Level Design (LLD) package covering all infrastructure layers required for the initial deployment:

•  Meet-Me Room (MMR) / Carrier Hotel architecture and cage layout;

•  MaiaEdge PBC hardware design — placement, mounting, power, and cabling specifications;

•  Fiber ingress and building entry point design;

•  Distribution layer topology and interconnect model; and

•  Switch fabric integration — architecture and uplink design.

END-TO-END CONNECTIVITY MODEL Carrier → MMR → PBC → Dark Fiber → Building → PBC → Switch Fabric

2.2  Fiber & Infrastructure Design

Requirements definition will cover:

•  Dark fiber ingress into the MMR and associated ODF cross-connect model;

•  Diverse fiber paths (A/B routes) to each building for high-availability design; and

•  Interbuilding dark fiber mesh topology.

Design deliverables will include:

•  Building-to-building connectivity model (partial or full mesh, based on cost/scale trade-off);

•  Fiber path diversity and routing assumptions documentation; and

•  Defined handoff points between fiber provider, MMR, and each OWNER building.

2.3  MaiaEdge Infrastructure Design

CONTRACTOR will define the hardware architecture across all sites:

•  Dual cage architecture within the MMR — Primary and Secondary;

•  Dual PBC deployment per cage — Primary / Secondary failover model;

•  Symmetric connectivity from all PBCs to buildings — no single points of failure;

•  PBC placement, power, and connectivity design within each OWNER building; and

•  Integration specifications between PBC and switching fabric.

2.4  Expansion Architecture (Up to 65 Buildings)

CONTRACTOR shall develop a scalable network CPE architecture framework in parallel with Phase 1 design, covering:

•  Fiber expansion model — incremental fiber provisioning as new buildings are added;

•  Mesh and interconnect strategy — partial to full mesh transition thresholds;

•  Capacity planning assumptions — bandwidth, port density, and PBC scaling; and

•  Modular deployment approach — standardized build-out templates per building.

2.5  Interface Coordination

CONTRACTOR shall coordinate across all infrastructure interface parties, including:

•  Dark fiber provider — critical dependency; will drive off-site routing and on-site delivery schedule;

•  Carrier coordination — based on current engagement model; inputs required for design assumptions; and

•  Installation partners — constructability feedback and duration estimate inputs.

Coordination activities include: regular design interface meetings, cross-party alignment sessions, and interface block diagram maintenance.

•  CONTRACTOR and [Pearce] will enter into mutually agreed non-disclosure agreements with all project vendors whose information is material to the scope of this SOW No.1

CONTRACTOR is authorized to subcontract [Pearce Services and/or CBRE] for portions of this scope related to physical infrastructure design.

2.6  Owner-Provided or Builder Data Required Information

OWNER will provide the following:

•  OSP Engineering Data

›  Geospatial OSP fiber routing plans aligned to site layout

›  Conduit pathway requirements and alignment

›  Handhole / vault placement recommendations

›  Building entry location definition

›  Cable routing and segmentation plans

›  Cable sizing and allocation (strand-level backbone definition)

›  Splice enclosure locations and design

›  Preliminary splice matrices

›  Diversity validation (A/B physical separation)

•  ISP Engineering Data

›  Telecom room layouts (MMR, BDF, MDF, IDF as applicable)

›  ODF layout and rack elevations

›  Fiber pathway design within buildings (tray / riser coordination)

›  Entrance → distribution room routing plans

›  A/B pathway separation validation within building

›  Data hall fiber distribution design (aligned to actual hall layouts)

›  End-of-row / top-of-rack distribution layouts

›  Tenant-ready distribution framework (if applicable)

•  Fiber Systems Engineering & Documentation

›  Strand-level fiber assignments

›  Final splice matrices

›  ODF port assignments

›  Patch panel layouts

›  Cross-connect mapping

›  Pre-terminated trunk cable schedules

›  Labeling schema implementation (input may be required from OWNER team)

›  Fiber naming conventions, finalized (input may be required from OWNER team)

›  Documentation structure for fiber management system (input may be required from OWNER team)

•  Construction Coordination & Technical Oversight (Design-Phase Support)

›  Participation in coordination meetings (GC, civil, MEP trades, low-voltage contractors)

›  Review of contractor submittals

›  Validation of installation against design intent

›  Field issue resolution support

›  Design clarification responses

›  Punch list support

›  Readiness reviews prior to testing / turnover

•  Site & Building Data

›  Site master plan (CAD / BIM)

›  Building floorplans

›  Telecom Hotel — room and / or cage locations and sizes

›  Data Halls — room and / or cage locations and sizes

SECTION  03

DELIVERABLES & TENTATIVE DELIVERY SCHEDULE

All deliverables are structured against a T+0 engagement start date. The table below defines each deliverable, its category, and its delivery milestone. All dates are based upon access to the information defined in Section 8 within the timeframes set forth therein.

| DELIVERABLE | CATEGORY | Date |
| --- | --- | --- |
| Kickoff Meeting — Agenda, Attendees, Decision Log | Project Initiation | T+0 (Day 1) |
| Technical Input Request — Required data from OWNER / fiber provider | Project Initiation | T+0 (Day 1) |
| Baseline Architecture Assumptions Document | Design Foundation | T+2 weeks |
| Interface Block Diagram (Fiber Provider / Carrier / OWNER / MaiaEdge) | Design Foundation | T+2 weeks |
| Phase 1 Low-Level Design (LLD) — All 9 Data Halls | Phase 1 Design | T+4 weeks |
| MMR / Carrier Hotel Architecture Design Package | Phase 1 Design | T+4 weeks |
| Building Connectivity Design — Per-building topology | Phase 1 Design | T+4 weeks |
| Interbuilding Fiber Mesh Design | Phase 1 Design | T+4 weeks |
| Bill of Materials (BOM) — Phase 1, equipment & fiber | Procurement Readiness | T+6 weeks |
| Material Takeoff (MTO) — Structured by building and layer | Procurement Readiness | T+6 weeks |
| Long-Lead Item Identification & Vendor Recommendation | Procurement Readiness | T+6 weeks |
| Building Infrastructure Specifications | Procurement Readiness | T+6 weeks |
| Fiber Design & Routing Assumptions Document | Procurement Readiness | T+6 weeks |
| MaiaEdge PBC Deployment Specifications (all sites) | Procurement Readiness | T+6 weeks |
| Vendor-Neutral Equipment Specifications & Data Sheets | Procurement Readiness | T+6 weeks |
| Expansion Architecture Document (to 65 buildings) | Expansion Planning | T+8 weeks |
| Capacity Planning Model — Bandwidth, port density, PBC scale | Expansion Planning | T+8 weeks |
| Construction-Ready Handoff Package — Phase 1 | Execution Prep | T+12 weeks |
| Installation Duration Estimates (per building) | Execution Prep | T+12 weeks |
| High-Level Cost Model — Infrastructure, Equipment, Deployment | Execution Prep | T+12 weeks |
| GMP / NTE Readiness Package | Commercial Enablement | T+12 weeks |

SECTION  04

PROJECT MILESTONES

| MILESTONE | DELIVERABLE GATE | WEEK |
| --- | --- | --- |
| M1 — Engagement Launch | Technical inputs received; kickoff complete; assumptions baseline published | Week 1 |
| M2 — Architecture Foundation | Interface Block Diagram approved; LLD scope locked | Week 2 |
| M3 — Phase 1 LLD Complete | All 9 Data Hall designs complete and under review | Week 4 |
| M4 — Procurement Package Complete | BOM, MTO, specs, and long-lead items delivered | Week 6–8 |
| M5 — Expansion Design Complete | 65-building architecture and capacity model delivered | Week 8 |
| M6 — Construction Handoff (~60% Engineering) | Construction-ready package, cost model, GMP readiness | Week 12 |

SECTION  05

ROLES & RESPONSIBILITIES

5.1  Team Structure

The goal is not to operate under rigid roles, but rather to maintain an agile process and minimal risk implementation throughout the engineering phase.

| ROLE | INDIVIDUAL / PARTY | RESPONSIBILITIES |
| --- | --- | --- |
| Engagement Lead | CONTRACTOR — Senior Network Architect | Overall accountability, commercial alignment, escalation point, OWNER executive relationship |
| Engineering Lead | CONTRACTOR — Senior Network Architect | Technical design ownership, LLD delivery, peer review coordination |
| PBC Integration Specialist | CONTRACTOR — Hardware Engineering | PBC deployment specs, hardware design, integration with switching fabric |
| Fiber Design Lead | CONTRACTOR / Third-Party PE | Dark fiber design, path diversity, interbuilding mesh, ODF cross-connect model |
| Project Coordinator | CONTRACTOR | Schedule tracking, milestone management, interface meeting coordination, document control |
| OWNER Technical POC | OWNER | Provide site requirements, review deliverables, approve design assumptions, interface with fiber provider |
| Dark Fiber Provider | TBD | Off-site fiber routing, on-site delivery, handoff point coordination |
| Installation Partner | TBD | Constructability input, duration estimates, site survey coordination |

SECTION  06

INTERFACES & DEPENDENCIES

| INTERFACE PARTY | DEPENDENCY | CRITICALITY | REQUIRED BY |
| --- | --- | --- | --- |
| Dark Fiber Provider | Off-site routing plan, on-site fiber delivery schedule, handoff point confirmation | Critical | T+1 week |
| Nexus Hubbard Carrier, LLC | Phase 1 building list (9 Data Halls and Carrier Hotel), MMR requirements, client-specific requirements | Critical | T+0 |
| Carrier Corporation / Third Party | Carrier coordination status; assumptions for design basis | High | T+2 weeks |
| Installation Partner | Constructability input, site access assumptions, duration estimates | Medium | T+4 weeks |

SECTION  07

DESIGN BASIS & ASSUMPTIONS

•  Standardized, non-bespoke architecture applied uniformly across all 9 Phase 1 Data Halls and the Carrier Hotel

•  Dual-path (A/B) dark fiber design for high availability at all building entry points

•  Symmetric PBC architecture deployed consistently across MMR cages and all buildings

•  Partial or full mesh interbuilding connectivity — final topology selected based on cost / scale analysis

•  Carrier coordination is managed by an existing third party; inputs will be provided as-available

•  Client-specific requirements (if any) are assumed at high level and may evolve during engagement

•  All design outputs are vendor-neutral unless otherwise specified by OWNER

•  Phase 1 buildings and MMR location are assumed to be within the Hubbard, TX at OWNER’s campus

SECTION  08

TECHNICAL INPUTS REQUIRED AT T+0

The following inputs are required from OWNER and associated parties within the timeframe set forth in the table below:

| INPUT | OWNER | REQUIRED BY |
| --- | --- | --- |
| Confirmed list of 9 Phase 1 Data Halls and Carrier Hotel (addresses / building IDs) | Nexus | T+0 |
| MMR location, dimensions, and power / cooling constraints | Nexus | T+0 |
| Dark fiber routes and proposed handoff points | Fiber Provider | T+1 week |
| Carrier coordination status and point of contact | Nexus / Third Party | T+1 week |
| Any OWNER client-specific connectivity requirements | Nexus | T+2 weeks |
| Installation contractor point of contact | Nexus | T+3 weeks |
| Existing infrastructure drawings (if any) | Nexus | T+0 |

SECTION  09

EXCLUSIONS

The following are explicitly out of scope for this SOW No.1:

•  Procurement execution — placement of purchase orders or vendor contracts. Procurement of BOM materials, logistics coordination, and on-site storage are the responsibility of OWNER. Procurement support services including vendor recommendations, BOM preparation, and long-lead item identification are included in this SOW No.1 as deliverables; additional procurement execution support may be incorporated upon mutual agreement

•  Physical installation, construction, or site commissioning activities

•  Carrier-specific custom design work (unless separately scoped and agreed)

•  Operational or managed service design

•  Network management, monitoring platform, or NOC integration design

•  Any design activity dependent on inputs not received by the required dates above

SECTION  10

COMMERCIAL BASIS

This Statement of Work is governed by the terms set forth in the Letter Agreement.

•  A tentative budget allocation of the Letter Agreement not-to-exceed amount across engineering workstreams is provided to OWNER under the Letter Agreement

•  Deliverables will provide sufficient design maturity to support Guaranteed Maximum Price (GMP) discussions for subsequent phases

•  Phase 1 engineering completion (~60%) is designed to de-risk procurement and installation pricing

•  Expansion architecture work (Section 2.4) enables long-range portfolio planning and phased investment commitments

Future work beyond the scope of this SOW No.1, including expanded engineering phases, construction oversight, and operational services, will be addressed under the Definitive Agreement as referenced in the Letter Agreement or through the joint venture agreement being negotiated between CONTRACTOR and Pearce.

SECTION  11

SITE ACCESS & SAFETY

All safety and PPE requirements established by OWNER will be followed by CONTRACTOR and Pearce personnel when accessing the Hubbard, TX site. CONTRACTOR and Pearce will require access to the site to conduct business and coordinate with OWNER and associated vendors.

This document contains confidential and proprietary information of MaiaEdge Networks, Inc. and is intended solely for the recipient named above. Unauthorized disclosure, reproduction, or distribution is strictly prohibited.

Note to Contractor: Please provide full entity names.

Note to Nexus: Please confirm if you can provide the items provided for in this list.