NEXUS HUBBARD CAMPUS

Carrier Hotel Network — Phase 1
Meet-Me Room Cross-Connect Platform

Joint Proposal — MaiaEdge (Technology) + Pearce (Engineering Professional Services)

Prepared for: Nexus Data Centers, LLC
April 2026  |  Confidential Working Draft

Note to internal team: This is a working outline for the MaiaEdge + Pearce response to Nexus's informal quote request. Sections with [TBD] are placeholders to be completed after internal alignment and any clarifying conversations with Nexus. Nothing in this draft should be shared externally without review.

# Contents

1. Executive Summary

2. Understanding of the Opportunity

3. Solution Overview and Phasing

4. Phase 1 Scope — MMR Cross-Connect Platform

5. Division of Responsibility — MaiaEdge + Pearce

6. Future-Phase Optionality

7. Commercial Structure

8. Project Schedule and Delivery

9. Assumptions, Dependencies, and Exclusions

10. Clarifying Questions for Nexus

11. Team, Qualifications, and References

Appendices

# 1. Executive Summary

Nexus Hubbard is positioned to become the second-largest U.S. Internet Exchange Point by aggregated fiber, the network gravity center for a 7+ GW AI hyperscale campus, and a durable recurring-revenue platform built on interconnection. The starting point for that platform is a reliable, carrier-neutral Meet-Me Room (MMR) environment that can patch any carrier to any tenant on demand, at scale.

MaiaEdge and Pearce are pleased to submit this joint proposal for the Phase 1 MMR cross-connect platform in the Nexus Hubbard Carrier Hotel. MaiaEdge provides the network architecture, active equipment, and operational tooling; Pearce provides engineering, racks, fiber layout, cabling, and field deployment. Together we deliver a single point of accountability from design through turn-up.

## Why MaiaEdge + Pearce

Single-team accountability: one integrated design, one deployment plan, one commissioning handoff.

Phase 1 done right, Phase 2+ pre-engineered: the MMR we build supports future IXP fabric, backbone DWDM, and campus east-west growth without re-work.

Carrier-neutral by design: open pathways, equal treatment of carriers, and tenant-portable cross-connects.

Matched to Nexus's commercial model: platform supports cross-connect, carrier cage leasing, IX participation, dark fiber, and wavelength services as Nexus elects to monetize each.

# 2. Understanding of the Opportunity

Our read of the two Nexus-authored reference documents (Carrier Hotel Basis of Design, Dec 2025; Fiber & Interconnection Strategy, Feb 2026) frames the opportunity as follows:

## 2.1 Facility profile (from BoD)

487,500 SF single-story carrier hotel; 50 MW IT load across five 10 MW phases.

~3,500 cabinets, 500+ tenant organizations, month-to-month lease flexibility.

Two independent Meet-Me Rooms (MMR-A and MMR-B), 12,000 SF each, with diverse fiber routing.

Dedicated IXP Equipment Room (2,000 SF); Cross-Connect Fields (8,000 SF); Carrier Cages (15,000 SF).

Two diverse Fiber Entry Rooms (FER-A and FER-B), 500 SF each, at opposite ends of the building.

2N power to carrier cages; N+1 chilled-water cooling; Tier-4 physical security on MMR entries.

Compliance baseline: ANSI/TIA-942, TIA-568, TIA-569, TIA-606-C, TIA-607-B, TIA-758, BICSI 002/TDMM.

## 2.2 Interconnection ambition (from Strategy doc)

~11,600 aggregated fiber strands at full buildout — ranked #2 U.S. IXP behind Ashburn.

13+ carriers with NDAs (Verizon, AT&T, Uniti, Databank, Fidium, FiberLight, Zayo, Lumen, Segra, Astound, NextLink, Flow Networks in progress).

Radial backbone to Waco, Corsicana, Hillsboro, Hubbard — 2,880 fibers per route into DFW, Houston, Austin, San Antonio, and beyond.

Nexus Data Centers, LLC pursuing CLEC and SPCOA designation with the Texas PUC.

Target services: private peering, public peering (IXP), cross-connects, dark fiber, wavelength, and managed network services.

## 2.3 Phase 1 ask (confirmed with Nexus)

Nexus has requested a quote for basic cross-connect capability — the ability to patch any carrier handoff to any tenant cabinet through the MMRs. This proposal is scoped tightly to that Phase 1 outcome and explicitly preserves optionality for IXP switching, backbone DCI, and campus east-west fabric in later phases.

# 3. Solution Overview and Phasing

We propose a four-phase roadmap. Only Phase 1 is priced in this response; Phases 2-4 are described to demonstrate that Phase 1 design decisions protect future optionality.

| Phase | Scope | Primary Driver | MaiaEdge Role | Pearce Role |
| --- | --- | --- | --- | --- |
| 1 — MMR Cross-Connect | Passive + active carrier-to-tenant patching across MMR-A/B | Launch revenue: cross-connects online | Fiber termination platform, management/OSS, [optional] active L1/L2 cross-connect fabric | Racks, cable tray, fiber layout, terminations, labeling, commissioning |
| 2 — IXP Fabric | Public peering LAN, route servers, IX portal | Monetize multilateral peering | Peering switch platform, route-server stack, IX automation | Rack/stack, interconnects to MMRs, cabling to peering carriers |
| 3 — Backbone DCI | DWDM / coherent optics on the 4 radial routes | Wavelength and transport services | Optical line systems, transponders, network management | OSP splicing coordination, ILA huts, rack/stack |
| 4 — Campus East-West | High-capacity DCI to AI halls and Neocloud clusters | AI traffic support, hyperscaler tenants | 400G/800G spine-leaf or DCI platform, segmentation | Campus fiber plant build-out, cabling, splicing |

# 4. Phase 1 Scope — MMR Cross-Connect Platform

## 4.1 Outcome Nexus receives

Any-to-any carrier-to-tenant cross-connect capability across MMR-A and MMR-B on day one of Phase 1 IT load.

High-density, labeled, test-certified fiber termination infrastructure that scales to the ~11,600-strand target.

A managed inventory of every strand, patch, and port — queryable by Nexus operations and auditable for tenants.

Diverse, carrier-neutral pathways from FER-A/FER-B to MMR-A/MMR-B, with redundancy for any single fiber path.

A documented, repeatable provisioning process for new cross-connect orders — from carrier handoff to tenant cabinet.

## 4.2 Functional requirements

Support single-mode fiber cross-connects at LC and SC termination (extendable to MPO as needed).

Support copper cross-connects where required (Cat 6A minimum).

Dual MMR topology with diverse paths: no single fiber path, panel, or pathway can sever carrier-to-tenant reach.

Provisioning under Tier-4 access control: cross-connect work executed by authorized personnel, logged, with escort where Nexus policy requires.

Inventory and labeling compliant with ANSI/TIA-606-C.

Capacity planning that assumes 50% fill at initial install, 100% fill at Phase 1 buildout (per BoD pathway sizing).

## 4.3 Technical architecture (proposed)

We will finalize the architecture jointly with Nexus, but the proposed Phase 1 reference design is:

Carrier handoffs land in carrier cages and terminate on MaiaEdge high-density fiber distribution panels (HD-FDPs) within MMR-A or MMR-B as elected by each carrier.

Tenant hand-offs terminate on matching HD-FDPs within the MMR closest to the tenant suite.

Cross-connects ride dedicated overhead ladder tray (Pearce scope) between carrier panels and tenant panels. Patch cords are managed via D-rings and waterfall adapters with controlled bend radius.

An MMR-A to MMR-B interconnect trunk (minimum 864-strand, split across ≥3 feet of pathway diversity) ensures any carrier in MMR-A can reach any tenant in MMR-B and vice versa.

[Option A — Passive only] All cross-connects executed manually by certified field techs, tracked in the MaiaEdge DCIM/inventory platform.

[Option B — Passive + Active L1/L2 fabric] An MaiaEdge-managed optical/Layer-2 cross-connect fabric provides software-driven provisioning for tenants wanting elastic connectivity (VLAN/EVPL) without waiting on physical patching. Differentiates Nexus vs. legacy carrier hotels. [To confirm with Nexus commercial team.]

## 4.4 MaiaEdge deliverables

Phase 1 low-level network design document, including MMR floor plans, panel layouts, and cross-connect pathways.

Bill of materials for all MaiaEdge-supplied equipment (fiber distribution panels, splice modules, patch cords, labeling system, [optional] active cross-connect switches).

DCIM / cross-connect inventory and provisioning platform — seeded with Phase 1 fiber plant and carrier handoffs.

Factory acceptance testing and shipping coordination.

Commissioning, turn-up, and as-built documentation hand-off.

Knowledge transfer and training for Nexus and/or Pearce field operations staff.

## 4.5 Pearce deliverables

MMR and Fiber Entry Room physical layout engineering (racks, ladder tray, fiber pathways, grounding).

Rack and cabinet installation per MaiaEdge panel plan.

Inside plant (ISP) fiber cabling from FER-A/FER-B to MMR-A/MMR-B, including any MMR-A ↔ MMR-B trunking.

Fiber splicing, termination, and bidirectional OTDR + insertion-loss testing to TIA-568 thresholds.

TIA-606-C labeling of racks, panels, ports, and fibers.

Coordination with carrier OSP providers at the FER demarcation.

Site supervision, safety, and project management during physical install.

# 5. Division of Responsibility — MaiaEdge + Pearce

The table below is a starting RACI for Phase 1. We will refine it jointly during kickoff.

| Work Stream | MaiaEdge | Pearce | Nexus |
| --- | --- | --- | --- |
| MMR network architecture | Responsible | Consulted | Approves |
| Equipment specification (panels, patches, DCIM, active elements) | Responsible | Consulted | Approves |
| Fiber pathway engineering (tray, conduit) | Consulted | Responsible | Approves |
| Rack and cabinet install | Informed | Responsible | Approves |
| Inside-plant fiber build and splicing | Informed | Responsible | Approves |
| Testing and certification (ISP fiber) | Informed | Responsible | Approves |
| DCIM / inventory platform stand-up | Responsible | Informed | Approves |
| Cross-connect provisioning workflow (process design) | Responsible | Consulted | Approves |
| Commissioning and turn-up | Responsible | Responsible | Approves |
| As-built documentation | Responsible | Contributes | Owns upon handoff |
| Phase 1 operations (post-handoff) | Optional (managed) | Optional (dispatch) | Owns |

# 6. Future-Phase Optionality

Phase 1 is priced as a standalone scope. The decisions we make in Phase 1 — panel density, pathway sizing, DCIM data model, and MMR-to-MMR trunking — are chosen specifically to avoid re-work when Nexus is ready for Phases 2-4. We will flag any decision point where Phase 1 cost could be reduced at the expense of Phase 2+ readiness so Nexus can make the commercial trade-off explicitly.

Phase 2 (IXP fabric): reserved rack positions in the IXP Equipment Room; MMR handoffs sized for peering-router uplinks.

Phase 3 (Backbone DCI): FER-A/FER-B pathway sizing preserves capacity for DWDM line systems on Waco, Corsicana, Hillsboro, Hubbard routes.

Phase 4 (Campus east-west): MMR-to-AI-hall pathway allowances included in Phase 1 pathway sizing; no re-tray required.

# 7. Commercial Structure

This section will be finalized once scope is confirmed. Proposed structure:

One-time CapEx: MaiaEdge equipment (line-item BOM), Pearce engineering + installation labor, materials, test and turn-up.

Optional recurring OpEx: DCIM/inventory platform subscription, managed cross-connect ops, remote-hands tiers.

Milestone-based billing tied to: design acceptance, equipment delivery, installation complete, commissioning accepted, as-builts delivered.

Price validity and change-order mechanism: [TBD — 60/90 days recommended].

Warranty: [TBD — equipment manufacturer warranty pass-through + 12-month workmanship on installed plant].

[TBD — Pricing BOM and labor estimate to be inserted once the Phase 1 scope is locked.]

# 8. Project Schedule and Delivery

Indicative milestones (to be tightened against Nexus's Phase 1 IT-load target date):

T+0: Contract award and kickoff.

T+2 weeks: Joint design workshop with Nexus, MaiaEdge, Pearce.

T+4-6 weeks: Phase 1 low-level design issued for approval; long-lead equipment ordered upon approval.

T+10-14 weeks: Rack, tray, and pathway install complete (Pearce).

T+12-16 weeks: Fiber plant terminated and tested; MaiaEdge panels and DCIM online.

T+14-18 weeks: Commissioning, cross-connect provisioning workflow validated, as-builts delivered.

T+16-20 weeks: Operational handoff; optional managed services engage if elected.

[TBD — align to Nexus's construction critical path and any anchor-tenant commitments.]

# 9. Assumptions, Dependencies, and Exclusions

## 9.1 Assumptions

Building shell, MEP, and security systems are delivered per the December 2025 Basis of Design and are complete before MaiaEdge/Pearce install begins.

OSP fiber from carriers terminates in FER-A / FER-B per the Nexus carrier-neutral pathway model; carrier demarcation responsibilities end at the FER.

Nexus provides site access, escort, and security credentials for MaiaEdge and Pearce personnel per Tier-4 MMR policy.

Power, cooling, and fire protection in MMR-A/MMR-B are operational and commissioned prior to equipment turn-up.

Pathway sizing in Phase 1 matches the BoD (24" wide ladder tray, 50% fill target).

## 9.2 Dependencies (on Nexus)

Final carrier roster and handoff format (LC/SC/MPO, strand count) per carrier.

Initial tenant roster and cabinet assignments for Phase 1 IT load.

DCIM/inventory integration requirements (if any existing Nexus system must be interoperable).

Security and visitor-management procedures for field crews.

Target cutover date for Phase 1 IT load.

## 9.3 Exclusions

Outside plant fiber from the property line to FER-A/FER-B (carrier scope).

Building electrical, mechanical, fire protection, or security systems (separate trades).

IXP switching fabric, backbone DWDM, and campus east-west DCI (Phases 2-4, not priced in this response).

Tenant-side in-cabinet cabling beyond the tenant demarcation panel.

Permits, bonds, and regulatory filings associated with Nexus's CLEC/SPCOA designation.

# 10. Clarifying Questions for Nexus

We recommend a 60-90 minute working session to resolve the following before we finalize pricing. Where answers are unavailable today, we will price to a reasonable Phase 1 baseline and note the assumption explicitly.

Confirmed Phase 1 IT-load target date and the anchor tenant(s) that drive it.

Should Phase 1 include the optional active L1/L2 cross-connect fabric (software-defined interconnect), or passive-only?

Does Nexus want MaiaEdge and/or Pearce to operate the cross-connect service post-install (managed ops, remote hands) or hand off to Nexus personnel?

Existing DCIM / OSS tooling at Nexus — any mandatory integrations?

Carrier handoff standard (LC/SC/MPO, strand count per carrier, copper handoffs if any)?

Initial tenant mix — portion of single-cabinet vs. multi-cabinet vs. hyperscaler peering deployments?

Phasing alignment — is the 10 MW Phase 1 IT load the cross-connect sizing driver, or is it tenant count / carrier count?

Preferred commercial model for cross-connect revenue: flat, metered, per-port, or tenant-owned strands?

Budget envelope or not-to-exceed, if any.

Evaluation timeline and decision criteria.

# 11. Team, Qualifications, and References

[TBD — to be completed by MaiaEdge and Pearce business development teams.]

MaiaEdge project sponsor and delivery lead.

Pearce project sponsor and delivery lead.

Joint steering committee and escalation path.

Relevant reference projects — carrier hotels, IXP builds, hyperscale DCI.

Certifications and insurance.

# Appendices

A. Phase 1 BOM (MaiaEdge equipment).

B. Pearce labor and materials estimate.

C. MMR reference drawings and pathway diagrams.

D. Draft Master Services Agreement terms.

E. Draft Statement of Work for Phase 1.

F. Joint team biographies and reference projects.